## ProjectSchedule
UIRI INVENTORY MANAGEMENT SYSTEM DATABASE PROJECT
Makerere University |  | Project Start: | 2026-06-15
Database Project Team: |  | Today: | 2026-06-28
By Keith, Tracy & Deo |  | Display Week: | 1 |  |  | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20
[50 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 |  |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | time axis 2026-06-15 to 2026-07-26
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | [42 empty] | S | S | S | M | T | W | T | S | S | S | M | T | W | T | time axis 2026-06-15 to 2026-07-26
Phase 1: Project Initiation and Requirements
Supervisor briefing and scope confirmation | Keith, Tracy & Deo | 100% | 2026-06-15 | 2026-06-15 | 1 | bar: 2026-06-15
UIRI inventory process study | Keith & Tracy | 100% | 2026-06-15 | 2026-06-17 | 3 | bar: 2026-06-15 to 2026-06-17
Stakeholder and user requirements gathering | Tracy & Deo | 100% | 2026-06-16 | 2026-06-19 | 4 | bar: 2026-06-16 to 2026-06-19
Review of project brief and research files | Keith | 100% | 2026-06-17 | 2026-06-19 | 3 | bar: 2026-06-17 to 2026-06-19
Proposal restructuring and approval draft | Keith & Tracy | 100% | 2026-06-18 | 2026-06-21 | 4 | bar: 2026-06-18 to 2026-06-21
Phase 2: Requirements Analysis and SRS
Problem analysis and business rules | Keith, Tracy & Deo | 100% | 2026-06-22 | 2026-06-23 | 2 | bar: 2026-06-22 to 2026-06-23
SRS preparation | Tracy | 100% | 2026-06-22 | 2026-06-26 | 5 | bar: 2026-06-22 to 2026-06-26
Use case identification | Deo & Tracy | 100% | 2026-06-24 | 2026-06-27 | 4 | bar: 2026-06-24 to 2026-06-27
Inventory categories and department mapping | Keith & Deo | 100% | 2026-06-23 | 2026-06-27 | 5 | bar: 2026-06-23 to 2026-06-27
Security requirements and audit review | Keith | 85% | 2026-06-27 | 2026-06-28 | 2 | bar: 2026-06-27 to 2026-06-28
Phase 3: Database Design and Documentation
Entity identification and relationship mapping | Keith | 100% | 2026-06-29 | 2026-06-30 | 2 | bar: 2026-06-29 to 2026-06-30
Data dictionary development | Tracy & Deo | 100% | 2026-06-30 | 2026-07-02 | 3 | bar: 2026-06-30 to 2026-07-02
Conceptual ERD preparation | Keith & Deo | 100% | 2026-06-30 | 2026-07-03 | 4 | bar: 2026-06-30 to 2026-07-03
Logical ERD and 3NF normalization | Keith | 100% | 2026-07-02 | 2026-07-04 | 3 | bar: 2026-07-02 to 2026-07-04
Extended ERD review and corrections | Keith, Tracy & Deo | 80% | 2026-07-04 | 2026-07-05 | 2 | bar: 2026-07-04 to 2026-07-05
Phase 4: Database Implementation
Physical schema creation in MySQL | Keith | 100% | 2026-07-06 | 2026-07-07 | 2 | bar: 2026-07-06 to 2026-07-07
Primary keys, foreign keys and constraints | Keith & Deo | 100% | 2026-07-07 | 2026-07-08 | 2 | bar: 2026-07-07 to 2026-07-08
Campus, department and category seed data | Tracy | 95% | 2026-07-08 | 2026-07-09 | 2 | bar: 2026-07-08 to 2026-07-09
Authentication and RBAC tables | Keith | 85% | 2026-07-09 | 2026-07-10 | 2 | bar: 2026-07-09 to 2026-07-10
Database integrity review | Keith, Tracy & Deo | 70% | 2026-07-10 | 2026-07-12 | 3 | bar: 2026-07-10 to 2026-07-12
Phase 5: Application Modules, Testing and Documentation
Inventory item and asset instance module | Keith & Tracy | 0% | 2026-07-13 | 2026-07-15 | 3 | bar: 2026-07-13 to 2026-07-15
Stock in, stock out and transfer module | Keith & Deo | 0% | 2026-07-14 | 2026-07-16 | 3 | bar: 2026-07-14 to 2026-07-16
Supplier, dashboard and reports module | Tracy & Deo | 0% | 2026-07-15 | 2026-07-17 | 3 | bar: 2026-07-15 to 2026-07-17
Security, audit trail and validation checks | Keith | 0% | 2026-07-17 | 2026-07-18 | 2 | bar: 2026-07-17 to 2026-07-18
System testing and correction | Keith, Tracy & Deo | 0% | 2026-07-18 | 2026-07-19 | 2 | bar: 2026-07-18 to 2026-07-19
Phase 6: Presentation and Final Submission
Final proposal and SRS packaging | Tracy | 0% | 2026-07-20 | 2026-07-21 | 2 | bar: 2026-07-20 to 2026-07-21
ERD and UML diagrams finalization in Visio | Deo | 0% | 2026-07-20 | 2026-07-22 | 3 | bar: 2026-07-20 to 2026-07-22
User manual and final project report | Keith & Tracy | 0% | 2026-07-21 | 2026-07-23 | 3 | bar: 2026-07-21 to 2026-07-23
Presentation slides and demonstration script | Keith, Tracy & Deo | 0% | 2026-07-22 | 2026-07-24 | 3 | bar: 2026-07-22 to 2026-07-24
Supervisor presentation and handover | Keith, Tracy & Deo | 0% | 2026-07-24 | 2026-07-24 | 1 | bar: 2026-07-24
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
UIRI Inventory Management System Work Plan
Project | Design and Development of a Web Based Inventory Management System for UIRI
Duration | 6 weeks
Start date | 2026-06-15
Presentation week | Week 6
Team Member | Project Role
Keith Paul Kato | Lead reporter, database design, normalization, schema implementation
Komukama Tracy | Requirements, SRS, documentation, supplier and report module support
Atuhiire Deo Kamate | Data dictionary, UML diagrams, testing and dashboard support
Supervisor | Mr. William Kakooza
Institution | Uganda Industrial Research Institute
University | Makerere University
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.